## Fee Breakdown
Square Footage - Existing		3,500 SF
Dollar per Square Footage		120 $/SF
Total Estimated Construction Costs		$420,000.00
Architecture Fees - Percentage of Construction		7.5%
Architecture/Engineering Fees		$31,500.00

		Approach (A)
%	Phase	% Const. Costs	Not-To-Exceed

5.0%	Phase 1: / Programming	0.4%	$1,575
10.0%	Phase 2: / Schematic Design	0.8%	$3,150
25.0%	Phase 3: / Design Development	1.9%	$7,875
35.0%	Phase 4: / Construction Documents	2.6%	$11,025
5.0%	Phase 5: / Bidding & Contract Negotiation	0.4%	$1,575
20.0%	Phase 6: / Construction Administration	1.5%	$6,300

100.0%	All Phases	7.5%	$31,500

## Hour Breakdown
Average ($/Hr) Billing Rate	$75.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people
Phase 1 - Programming	5.00%	$1,050.00	$1,050.00	14 hrs	0.7 wks	0.5 wks	0.4 wks	0.2 wks	0.2 wks
Phase 2 - Schematic	10.00%	$2,100.00	$3,150.00	28 hrs	1.4 wks	0.9 wks	0.7 wks	0.5 wks	0.4 wks
Phase 3 - Design Development	25.00%	$5,250.00	$8,400.00	70 hrs	3.5 wks	2.3 wks	1.8 wks	1.2 wks	0.9 wks
Phase 4 - Construction Documents	35.00%	$7,350.00	$15,750.00	98 hrs	4.9 wks	3.3 wks	2.5 wks	1.6 wks	1.2 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$1,050.00	$16,800.00	14 hrs	0.7 wks	0.5 wks	0.4 wks	0.2 wks	0.2 wks
Phase 6 - Construction Administration	20.00%	$4,200.00	$21,000.00	56 hrs	2.8 wks	1.9 wks	1.4 wks	0.9 wks	0.7 wks
	100.00%	$21,000.00	$21,000.00	280 hrs	14.0 wks	9.3 wks	7.0 wks	4.7 wks	3.5 wks

Architecture	5.0%	67%	$21,000.00
Structural	1.3%	17%	$5,250.00
Civil	1.3%	17%	$5,250.00
	7.50%	100.00%